|  |
| --- |
| HOUSING AND HOMELESSNESS WORKING GROUP: August 2015  |
| **GOAL: End Veteran Homelessness in Los Angeles** | **Agency or PoC** | **DEADLINE** | **% COMPLETED** |
| Develop strategies for homeless women veterans and their children | Megan Rodriguez & Ryan Williams | August 2015 | 80% |
|  |  |  |  |
| Develop strategies to support disabled vets that are income disqualified for supportive housing.  |  | November 2015 | 25% |
|  |  |  |  |
| Draft letter to support efforts for interjurisdictional agreements for LA County Housing Authorities.  |  | November 2015 | 0% |
|  |  |  |  |
| Create a list of resources for “soft good” move-in assistance for homeless veterans. Possibly include a big ask to IKEA.  |  | November 2015 | 0% |
|  |  |  |  |
| Draft a flyer with 3-5 things anyone can do to end veteran homelessness in LA | Hillary Evans | August 2015 | 100% |
|

|  |
| --- |
|  |

 |  |  |  |
| Draft a H&H letter of support for Feinstein’s letter regarding West LA Campus | Milo Peinemann | September 2015 | 50% |
|  |  |  |  |
| Draft letter for VA Master Plan with emphasis on encouraging housing for most vulnerable homeless veterans.  | Hillary Evans | September 2015 | 50% |
|  |  |  |  |
| Draft Policy Brief on other-than-honorably-discharged veterans, addressing obstacles, needs, and agencies that will address the needs. | Hillary Evans | August 2015 | 50% |
|  |  |  |  |
| Publish Policy Brief based on Peinemann/ Evans manifesto | Milo Peinemann & Nathan Graeser | August 2015 | 60% |
|  |  |  |  |
| Staff a policy intern to create handouts for each meeting with policy issues and opportunities to inform electeds, complete with who to contact, sample letters, and issue briefs, concentrating on Bills and Props that need support.   Build bridges among all the major partners addressing veteran homelessness.   | Nathan Graeser | August 2015 | 100% |
|  |  |  |  |
| Identify a source of funding for Coordinated Outreach Teams through CES to provide hotel vouchers for female veterans and female veterans with children. | Hillary Evans | August 2015 | 0% |
|  |  |  |  |
|  Follow up on SSVF and DPSS Collaboration in regards to General Relief and GROW in addition to changes in SSVF and VASH | Phil Bowers | August 2015 | 95% |
|  |  |  |  |
| Prop 41 updated information and NOFA dates and Policy Brief | Steve Renahan | October 2015 | 70% |
|  |  |  |  |
| Develop info system for pipeline buildings for outreach teams and agencies  | Hillary Evans | December 2015 | 10% |
|  |  |  |  |
| Comment on Housing Agency Plans for homeless veterans’ housing options  | Steve Renahan | September 2015 | 50% |
|  |  |  |  |
| Draft SSVF Policy Brief | Steve Renahan | October 2015 | 10% |
|  |  |  |  |
| Collaboratively with United Way, create marketing plan with material and endorsements to encourage housing veterans and use of VASH Vouchers  | Steve Renahan | September 2015 | 100% |
|  |  |  |  |
| Comment on Prop 41 Guidelines draft | Steve Renahan | December 2014 | 100% |
|  |  |  |  |
| Broaden H& H Group participation to include electeds’ staff and administrators of all large veteran homeless programs, including GPD, SSVF, VASH, HVI, S+C, and VHHP | Hillary Evans & Steve Renahan | May 2015 | 100% |