|  |
| --- |
| Legal and Reentry  |
| **OVERALL GOAL:** **Insert Overall Goals of Working Group** (Simple, Measurable and Achievable)\*Break this out into multiple goals below | **% COMPLETED** |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Train 80 civilian attorneys to handle veteran cases | Dwight | 12/31/15 | 60% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Have each member of the working group identify a project he/she would like to work on | Dwight & Jodi | 5/1/15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Bring awareness to veteran-specific legislation | Jodi | 12/31/15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Initiate a veteran peer support certification program for CAWorked with group of PHD students to crate CORE competency Curricullum –fiinished in Sept 2015 | Jodi | 12/31/16 | 50% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
| Set up meeting to Develop veteran resource cards—Senator Liu law enforcement summit—all agencies in her district to get a veteran resource card, contact with Sheriff dept to customize for their vast area Set up meeting Danielle James Commander Frazer @ Patriotic Hall  | Jodi-Danielle, Megan | 8/1/15 7/31/1510.6.15 | 100% Senator Liu district100% Sheriff dept specifcs vet cards-to be continued with Sheriff dept |
|

|  |
| --- |
| **INDIVIDUAL GOALS**  |
| Develop veteran resource dards LA Sheriff Dept |   |  |  |

Met with A?S Michael Rothans, commander Kelly Fraser assigned to project Sept 15, 2015 We hope the sheriff dept will take the lead for LA county10.14—Asked Megan Rodriquez with Senator Lui’s office to confer with Danielle to bring the rest of the law enforcement entities on for the resource cards once we have the sheriff dept.**INDIVIDUAL GOALS**  | **Agency or POC****Jodi Danielle James** | **DEADLINE****9/15/16** | **STATUS****30%** |
|  Parking citation program-contact CA-Camilo Cruz Mayor’s office Greg Homeless Director (Joseph Chicas & Maribel Marin took the project and are suppose to be working with the city)9/9/2015 Brian Binkley with the Mayor’s office attended our mee4ting—he is a vet with parking citations, he said he will do everything he can to push this forward—we sent him the proposals10.21.15 Unfortuantely we have never heard back from Brian Binkley—Joseph Chicas left the Mayor’s office—We need Nathan to intervene and Mr Castro!!!!! | Jodi, Maribel & Joseph Chicas & Brian BinkleyWE need USC’s intervention iwht this project as it has stalled!!! | 12/1/15 | 30% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Increase our membership—sent massive email to attorneys accredited to help veterans with benefits | Jodi | 2/19/15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Increase our membership—ongoing –engage each committee member to bring new members | Dwight & Jodi  |  |  |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Create attorney list to help veterans—sent massive email to accredited attorneys & attorneys who’ve attended committee with form to fill out with years in practice and areas of practice |  Jodi & Dwight | 2/19/16 | 20% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Help Coordinate Female Veteran Summit March 28 –getting female attorneys and handout for resources |  Jodi | March 28 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Distribute PC 1170.9 Posters/flyers/postcards/business cards thru out LA countyDistributed PC 1170.9 posters etc to Sacramento and to state-wide veteran justice committee 10.20.15 |  collaborative |  | 90% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Train Battle buddies and connect them with lawyers to help with ticket project—connected them to LACBA project | Jodi Dwight  | 1/27/15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Form sub-committee to gather and disseminate info regarding Prop 47 reducing certain felonies to misdemeanors & obtaining expungements.10.21.15 Added Paula Clamurro to subcommittee-she will be spearheading clinics for NLSLA for prop 47 |  JodiPaula Clamurro | 3/12/1510.14.15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Form sub-committee for female veteran issuesUPDATE-created TIP sheet for MSTDanielle Hanne and sub committee are expanding list of resources for female vets from 211 list |  JodiLaura et setDaniele Hanne | 5/13//159.9.15begun 10.14.15—deadline 10.14.16 | 100%100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Form sub committee for veteran financial literacy |  Shannon | 5/13/15 | 100% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Helping individual veterans with their legal issues—regularly get requests, always find them resolutions | Jodi & dwight  | ongoing |  |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Help spreads the word about PC 1170.9, PC 1001.80 new misdemeanor diversion program for military & veterans ID vets in CJ system—connected Sacramento PD with SD PD with LA PD (recently was able to have a LA county PD assigned for the project

|  |
| --- |
| **Mitchell J. Bruckner-head deputy who has sent our request to the administration of his office** |

—connected him with Stephanie Stone) Update Sept 2015 CALVET is sending info PC 858 which mandates the court use MIL 100 to ID vets which informs them about PC 1170.9, PC 1001.80 Also Jodi is trying to get it implemented in LA10.21.15 1. meeting with veteran entities to collaborate to provide services for vets in jail & court 2. Connected with Chief Public Defender Rod Kodman obtained all his materials on PC 858, PC 1170.9 PC 1001.80 got him on stte wide committee 3. Creating email for the LA Public Defendere Ron Brown asking his assistance to implement PC 858, PC 1001.80 and PC 1170.9 |  jodi | ongoing |  |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Initiate & explore possibility to create a program to help veterans with parole hearings---Jefferson Harwell—Judge Wright, SW law students Update Sept Jefferson Harwell left—have connected the SW studnets with Judge Eileen Moore who is doing a program to help viet nam vets with parole heairngs—they will attend training Seot 28 |  jodi | 12/31/15 | 20% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|  Initiate & explore possibility to create female veteran pods and resources for female vets at LA county jail as well as expand those for male vets July 31 had meeting with Sheriff administration agreed to have future meeting to insure progress10.21.15 meeting with veteran service entities to privde services to the jails |  Jodi , Sheriff dept Xavier & AS Terri McDonnell | ongoing | 10% |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|   |   |  |  |
| **INDIVIDUAL GOALS**  | **Agency or POC** | **DEADLINE** | **STATUS** |
|   |   |  |  |