|  |
| --- |
| WORKING GROUP STRATEGY - Families & Children Work Group February 11, 2015 |
| **OVERALL GOAL:** **Plan for the implementation of April, Month of the Military Child event that will be held at the LA Public Library on Saturday, March 28, 2015. Gain Work Group’s cooperation in participating in the program’s development and assign specific duties.**  | **OVERALL GOAL COMPLETED****40%** |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
|  Outreach to FRG’s and Family Assistance Programs to share info re. A,MOMC event. Also obtain participation of her agency’s Art Therapists as volunteers to work with the children in an activity.  | Erica Trejo,DiDi Hirsch CMHC | March 16, 2015 |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Work with the LA Public Library in confirming resources needed from Library staff in preparation of the event. | Edwin Rodarte, Deb Hayes, Gail Soffer  | On-going |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Explore donation of boxed lunches | Elena (Trader Joe’s)Luis South (Starbucks)  | On-going  |  -- |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Contact City Council Members for support of the AMOMC event |  Luis South |  |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Contact – Senator Holly Mitchell’s Office, Congress Member Karen Bass, Cal National Guard,  | Deborah Hayes | --- | DONE 100% |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Contact - Newport Yacht Club, Dodgers Baseball Club and Long Beach Aquarium | Gail Soffer  | March 3, 2015 |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Outreach to USC MSW student leaders to enlist volunteers for the event. (Military Caucus, Student Org, UPC and San Diego  | Deborah Hayes  | On-going |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Confirm activities and volunteer participant roles, confirm program agenda  | Deb Hayes, Gail Soffer  | March 11, 2015 |  |
| **TASK**  | **POC** | **DEADLINE** | **%COMPLETED** |
| Develop background informational sheet on AMOMC event  |  Deb Hayes  | Feb 15, 2015 |  100% |