|  |  |  |  |
| --- | --- | --- | --- |
| HOUSING AND HOMELESSNESS WORKING GROUP | | | |
| **OVERALL GOAL:**  **End Veteran Homelessness** | | | **33% COMPLETED** |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Comment on Prop 41 Guidelines draft | Steve Renahan | December 2014 | 100% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Draft Policy Brief on other-than-honorably-discharged veterans, addressing obstacles, needs, and agencies that will address the needs. | Hillary Evans | May 2015 | 5% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Create marketing plan with material and endorsements to encourage housing veterans and use of VASH Vouchers | Hillary Evans | May 2015 | 5% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Create standards for customer service when working with landlords based on PATH’s working group and come to consensus about how PATH and agencies can participate | Jonathan of PATH | June 2015 | 0% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Accelerate HACoLA VASH Leasing | Ryan | 4/5/15 | 0% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Follow up on SSVF and DPSS Collaboration in regards to General Relief and GROW in addition to changes in SSVF and VASH | Steve Renahan | 4/5/15 | 75% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Prop 41 updated information and NOFA dates and Policy Brief | Steve Renahan | 4/15/15 | 25% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Develop way for outreach teams and agencies to know what buildings are in pipelines | Hillary Evans | 12/15/15 | 10% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Comment on Housing Agency Plans to improve homeless veterans’ housing options | Steve Renahan | 9/30/15 | 50% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Create an action plan to streamline process of approval between landlords and applicants. |  |  | 0% |