|  |  |  |  |
| --- | --- | --- | --- |
| Legal and Reentry | | | |
| **OVERALL GOAL:**  **Insert Overall Goals of Working Group** (Simple, Measurable and Achievable)  \*Break this out into multiple goals below | | | **% COMPLETED** |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Train 80 civilian attorneys to handle veteran cases | Dwight | 12/31/15 | 60% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Have each member of the working group identify a project he/she would like to work on | Dwight & Jodi | 5/1/15 | 25% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Bring awareness to veteran-specific legislation | Jodi | 12/31/15 | 40% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Initiate a veteran peer support certification program for CA | Jodi | 12/31/15 | 70% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Develop veteran resource cards—Senator Liu law enforcement summit—all agencies in her district to get a veteran resource card, contact with Sheriff dept to customize for their vast area | Jodi-Danielle, Megan | 8/1/15 | 50% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Parking citation program-contact CA-Camilo Cruzm Mayor’s office Greg Homeless Director | Jodi | 12/1/15 | 60% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Increase our membership—sent massive email to attorneys accredited to help veterans with benefits | Jodi | 2/19/15 | 100% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Increase our membership—ongoing –engage each committee member to bring new members | Dwight & Jodi |  |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Create attorney list to help veterans—sent massive email to accredited attorneys & attorneys who’ve attended committee with form to fill out with years in practice and areas of practice | Jodi & Dwight | 2/19/16 | 20% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Help Coordinate Female Veteran Summit March 28 –getting female attorneys and handout for resources | Jodi | Maarch 28 | 100% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Distribute PC 1170.9 Posters/flyers/postcards/business cards thru out LA county | collaborative |  | 70% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Train Battle buddies and connect them with lawyers to help with ticket project—connected them to LACBA project | Jodi Dwight | 1/27/15 | 100% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Form sub-committee to gather and disseminate info regarding Prop 47 reducing certain felonies to misdemeanors & obtaining expungements. | Jodi | 3/12/15 | 100% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Distribute PC 1170.9 Briefs to defense entites –LA public defender, San Diego Public defender & law school legal clininc, Sacramento Public defender | jodi | 12/15 | 40% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Spread the word about Veteran DV programs both in LA & OC, help OC get certified –OC certified, poster done, LA working on poster | jodi | 8/15 | 70% |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Helping individual veterans with their legal issues—regularly get requests, always find them resolutions | Jodi & dwight | ongoing |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
| Help spreads the word about PC 1170.9, PC 1001.80 new misdemeanor diversion program for military & veterans ID vets in CJ system—connected Sacramento PD with SD PD with LA PD | jodi | ongoing |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
|  |  |  |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
|  |  |  |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
|  |  |  |  |
| **INDIVIDUAL GOALS** | **Agency or POC** | **DEADLINE** | **STATUS** |
|  |  |  |  |